## Risk_Treatment
CRITICAL RISKS
Risk ID | Risk Description | Risk Level | Treatment Strategy | Action Plan | Owner | Timeline | Status
R-01 | Unauthorized Access | Critical | Mitigate | Implement authentication & access control | Developer
R-06 | Deployment Errors | Critical | Mitigate | Introduce change approval process | Developer
R-08 | Change Management Failure | Critical | Mitigate | Establish formal change management workflow | Developer
HIGH RISKS
Risk ID | Risk Description | Risk Level | Treatment Strategy | Action Plan | Owner | Timeline | Status
R-02 | Data Breach | High | Mitigate | Implement encryption & data protection | Developer | Medium-term | Open
R-04 | Lack of Logging | High | Mitigate | Enable logging & monitoring | Developer | Medium-term | Open
R-05 | System Failure | High | Mitigate | Improve system reliability | Developer | Medium-term | Open
R-07 | Transaction Integrity | High | Mitigate | Implement transaction validation logic | Developer | Medium-term | Open
R-09 | Regulatory Non-Compliance | High | Mitigate | Align with compliance requirements | System Owner | Medium-term | Open
R-10 | Lack of Audit Readiness | High | Mitigate | Implement audit logging & documentation | System Owner | Medium-term | Open
R-13 | Data Integrity | High | Mitigate | Validate data consistency | Developer | Medium-term | Open
R-15 | Lack of Policies | High | Mitigate | Develop security policies | System Owner | Medium-term | Open
R-16 | ndefined Roles | High | Mitigate | Define roles & responsibilities | System Owner | Medium-term | Open