## Risk_Register
Risk ID | Risk Name | Category | Impact | Likelihood | Score | Risk Level | Existing Control | Gap | Remediation | Owner | Priority | Status | Detection Method | Target Date
R-01 | Unauthorized Access | Cybersecurity | 5 | 4 | 20 | Critical | None | No authentication mechanism implemented | Implement authentication system (JWT or session-based login with access enforcement) | Developer | High | Open | Monitoring unauthorized access attempts via logs (if implemented) | TBD
R-02 | Data Breach | Cybersecurity | 5 | 3 | 15 | High | Partial field-level encryption is implemented for selected PII fields | Sensitive customer data is not fully protected; some PII remains in plaintext and access restrictions are limited | Implement consistent encryption for all sensitive PII fields and restrict access to customer data based on least privilege | Developer | High | Open | Detect through database access reviews, security event monitoring, and investigation of suspicious data exposure indicators | TBD
R-03 | Weak Access Control | Cybersecurity | 4 | 4 | 16 | Critical | Basic middleware protections (e.g., CSRF, rate limiting) are partially implemented | No role-based access control (RBAC) or privilege restrictions are enforced across system components | Implement RBAC and enforce least privilege access control for all system roles and resources | Developer | High | Open | Review access control configurations and monitor unauthorized access attempts through logs | TBD
R-04 | Lack of Logging and Monitoring | Cybersecurity | 4 | 3 | 12 | High | Basic system-level logs are available | No centralized logging, no user activity tracking, and no monitoring or alerting mechanisms | Implement centralized logging system and enable monitoring and alerting for security events | Developer | High | Open | Not effectively detectable due to absence of logging and monitoring controls | TBD
R-05 | System Failure | Operational | 4 | 3 | 12 | High | Basic application structure and hosting environment are in place | No redundancy, failover, or system availability monitoring mechanisms | Implement system monitoring, uptime checks, and redundancy/failover mechanisms | Developer | High | Open | Detect via uptime monitoring tools and system health checks | TBD
R-06 | Deployment Errors | Operational | 4 | 4 | 16 | Critical | Basic development and deployment practices are in place | No formal testing, validation, or deployment controls before releasing code to production | Implement testing procedures, staging environment, and deployment validation controls | Developer | High | Open | Detect through system errors, failed transactions, and post-deployment issue monitoring | TBD
R-07 | Transaction Integrity Failure | Operational | 5 | 3 | 15 | High | Stripe payment processing is implemented | No validation or synchronization between payment completion and order creation in the system | Implement transaction validation logic and ensure order creation is tightly coupled with successful payment confirmation (e.g., webhook-based validation) | Developer | High | Open | Detect through reconciliation of payment records vs. database entries and monitoring of missing order confirmations | TBD
R-08 | Change Management Failure | Operational | 4 | 4 | 16 | Critical | Informal development practices exist, but no structured change control process | No formal change approval, review, or documentation process for system changes | Implement formal change management process including pull request workflow, approval controls, and change documentation | Developer | High | Open | Detect through code repository review, identifying direct commits without approval or change tracking | TBD
R-09 | Regulatory Non-Compliance | Compliance | 5 | 3 | 15 | High | Partial data protection measures and basic system controls are in place | System does not fully comply with data protection and privacy requirements due to missing controls (encryption, logging, access control, data retention) | Implement comprehensive data protection controls aligned with regulatory requirements (encryption, access control, logging, and data retention policies) | System Owner | High | Open | Detect through compliance reviews, audits, and regulatory assessments | TBD
R-10 | Lack of Audit Readiness | Compliance | 4 | 3 | 12 | High | Basic system functionality is operational, but no formal audit documentation or evidence management exists | No structured audit evidence, control documentation, or audit trail to support compliance verification | Establish audit documentation, implement evidence collection processes, and maintain control records aligned with audit requirements | System Owner | High | Open | Identified during internal audit reviews or external audit assessments | TBD
R-11 | Vendor Dependency | Third-Party | 3 | 3 | 9 | Medium | Third-party service (Stripe) is integrated and operational | High dependency on a single vendor without fallback or redundancy | Implement contingency planning and evaluate alternative payment options to reduce dependency risk | System Owner | Medium | Open | Detect through service availability monitoring and vendor performance tracking | TBD
R-12 | Vendor Security Risk | Third-Party | 3 | 3 | 9 | Medium | Trusted third-party services are used (e.g., Stripe) | No vendor security assessment or due diligence process is implemented | Perform vendor security assessments and establish a third-party risk management process | System Owner | Medium | Open | Detect through vendor security reviews, incident notifications, and third-party risk assessments | TBD
R-13 | Data Integrity | Data | 4 | 3 | 12 | High | Basic data storage and processing mechanisms are implemented | No data validation, reconciliation, or integrity checks across system processes | Implement input validation, data integrity checks, and reconciliation mechanisms between system components | Developer | High | Open | Detect through data validation checks, reconciliation processes, and identification of inconsistent records | TBD
R-14 | Data Retention | Data | 3 | 3 | 9 | Medium | Customer data is stored within the system database | No defined data retention or deletion policy for customer data | Establish and enforce data retention and deletion policies aligned with regulatory requirements | System Owner | Medium | Open | Detect through data audits and review of stored data against retention policies | TBD
R-15 | Lack of Policies | Governance | 4 | 3 | 12 | High | Basic operational practices are followed informally | No formal security, access control, data protection, or change management policies are documented | Develop and implement formal policies covering security, access control, data protection, and change management | System Owner | High | Open | Identified through governance review and absence of documented policies | TBD
R-16 | Undefined Roles | Governance | 4 | 3 | 12 | High | Basic roles exist (e.g., developer, system owner), but responsibilities are not formally defined | No clearly defined roles and responsibilities for risk ownership, control ownership, or approval processes | Define and document roles and responsibilities for system operations, risk management, and control ownership | System Owner | High | Open | Identified through governance review and lack of role definition in system operations | TBD